DEADLINE CALENDAR · FOR THURSDAY'S TEAM MEETING

Hypothalamus MRI Segmentation

NUDZ (Czech National Institute of Mental Health) × IFSA Prague Challenge Project, Spring 2026

Generated Sep 29, 2026  ·  Team: 3 members  ·  Proposal due Sun Oct 11, 23:59

# Before Thursday

From Jaison's kickoff email. All three items are per-person, not team-wide.

- Review shared materials — the Google Drive folder and Charley's autoseg GitHub repo. Flag anything unclear to raise Thursday.

- Stand up your own GitHub repo — create it, then post the link in the group chat before the meeting.

- Shortlist 3 R-CNN implementations — no pressure, picks can shuffle or merge once the team talks it through.

Dr. Ankit (image processing) joins Thursday's call — come with questions worth brainstorming live.

## R-CNN family — a starting menu, not a chosen set

Faster R-CNN · Mask R-CNN · Cascade R-CNN · Cascade Mask R-CNN · Hybrid Task Cascade (HTC) · PointRend · Sparse R-CNN · Grid R-CNN · Libra R-CNN

# This Sprint: Today → Proposal Due

Two weeks, two Thursday calls with Dr. Ankit, one hard deadline.

| Date | Event |
| --- | --- |
| Tue Sep 29 | Today |
| Wed Sep 30 | — |
| Thu Oct 1 | Team call 1: kickoff, roles + R-CNN share-out |
| Fri Oct 2 | Suggested due: Cover page & table of contents |
| Sat Oct 3 | — |
| Sun Oct 4 | Suggested due: Project details section |
| Mon Oct 5 | — |
| Tue Oct 6 | — |
| Wed Oct 7 | Suggested due: Product dev plan, Team log, Risks |
| Thu Oct 8 | Team call 2: proposal review w/ Dr. Ankit |
| Fri Oct 9 | Suggested due: full draft assembled + review |
| Sat Oct 10 | Final formatting & proofread |
| Sun Oct 11 | PROPOSAL DUE, 23:59 |

# Proposal Task Breakdown

Mapped to the rubric's 10 points. Owner column is intentionally blank — fill it in live on Thursday.

| Rubric Section | Points | Internal Due | Owner |
| --- | --- | --- | --- |
| Cover page & table of contents | 0.5 | Fri Oct 2 | TBD Thursday |
| Project details — background, objective, industry focus, value proposition | 1.5 | Sun Oct 4 | TBD Thursday |
| Product development plan — tech stack, MVP, logistics, timeline, scalability | 2.0 | Wed Oct 7 | TBD Thursday |
| Team collaboration log — role justifications, job descriptions, PM screenshot, action items, Team Diagnostic Worksheet | 2.0 | Wed Oct 7 | TBD Thursday |
| Risks & challenges — technical, market, regulatory, mitigations | 2.0 | Wed Oct 7 | TBD Thursday |
| Concluding remarks | 1.0 | Fri Oct 9 | TBD Thursday |
| AI-use disclosure (prompts + full output, Level 3) — gating, not separately scored | — | Fri Oct 9 | whoever used AI |
| Full draft assembled + team review pass | — | Fri Oct 9 | all 3 |
| Final formatting, page numbers, proofread | — | Sat Oct 10 | TBD Thursday |
| Submit |  | Sun Oct 11, 23:59 |  |
| Rubric total | 10.0 |  |  |

# Full Program Timeline

Weeks 3–15 per the IFSA phase structure, mapped to real dates.

| Wk | Dates | Phase | Notes / Milestones |
| --- | --- | --- | --- |
| 3 | Sep 21–27 | Phase 1: Project setup | — |
| 4 | Sep 28–Oct 4 | Phase 1: Project setup | Today (Sep 29) · Team call Thu Oct 1 |
| 5 | Oct 5–11 | Phase 2: Iterative dev + company feedback | Team call Thu Oct 8 · PROPOSAL DUE Sun Oct 11 |
| 6 | Oct 12–18 | Phase 2: Iterative dev + company feedback | — |
| 7 | Oct 19–25 | Phase 2: Iterative dev + company feedback | — |
| 8 | Oct 26–Nov 1 | Phase 2: Iterative dev + company feedback | — |
| 9 | Nov 2–8 | Update presentation to IFSA + company | Status update / feedback checkpoint |
| 10 | Nov 9–15 | Phase 3: Rework + documentation | — |
| 11 | Nov 16–22 | Phase 3: Rework + documentation | — |
| 12 | Nov 23–29 | Phase 3: Rework + documentation | Thu Nov 26 call lands on US Thanksgiving — confirm |
| 13 | Nov 30–Dec 6 | Phase 3: Rework + documentation | — |
| 14 | Dec 7–13 | Phase 4: Final delivery + handover | — |
| 15 | Dec 14–20 | Phase 4: Final delivery + handover | Final presentation ~Dec 17 |

■  Phase 1: Project setup      ■  Phase 2: Iterative dev + company feedback      ■  Update presentation to IFSA + company      ■  Phase 3: Rework + documentation      ■  Phase 4: Final delivery + handover

Assumption: week numbering is inferred by anchoring “Week 5 ends Sun Oct 11” (stated in the rubric) and counting Week 1 as starting Mon Sep 7. Confirm the real Week 1 start with Jaison or the IFSA calendar if this is off — everything above shifts by the same amount.

Heads up: the Week 12 Thursday call (Nov 26) lands on US Thanksgiving — worth confirming that one still happens.